# Background

# Late last year, Pfizer Inc. Finalized its $43 billion acquisition of Seagen Inc., representing the largest biopharmaceutical M&A transaction since AbbVie acquired Allergan in a $63 billion deal in 2019 and the cornerstone of Pfizer's efforts to rebuild its decimated oncology franchise following significant post-pandemic revenue declines. It effectively doubled Pfizer’s oncology pipeline to 60 programs and added Seagen’s four marketed antibody-drug conjugates (ADCs)-ADCETRIS, PADCEV, TIVDAK, and TUKYSA-to its portfolio. Pfizer funded the deal using some $31 billion in long-term debt, and another $8 billion in commercial paper, bringing its total debt load from $35.8 billion to $71.9 billion nearly 2x. The company expects Seagen's ADC franchise to deliver over $10 billion in risk-adjusted revenue by 2030, as well as about $1 billion in annual cost synergies by 2026, per Pfizer Inc. (2023a; 2023b). This is a simple strategic rationale: Pfizer is in danger of seeing nearly $17 billion of its revenue lost to patents expirations on products like Eliquis, Ibrance, and Xeljanz through 2030, and Seagen’s unique ADC linker-payload platform-complemented by Pfizer’s comprehensive antibody library-is intended to transition Pfizer to a global leader in precision oncology rather than a company in patent-expired decline.

# The issue making this transaction an interesting object for an ERM analysis is exactly the gulf between that strategic argument and the risks of executing it. Ultimately, the central question being addressed in this assessment isn’t whether acquiring Seagen “made sense” on paper-an idea well supported by a range of sources-but rather whether Pfizer can achieve the acquisition’s $10 billion revenue thesis in a fiercely competitive ADC landscape, managing the integration of 3,400-person science-led biotech into an 80,000-person global behemoth, navigating its significantly leveraged balance sheet, and operating within a U.S. Regulatory and reimbursement regime transformed by the IRA. The core risk is the interplay among these factors; for instance, an ambitious approach to capturing cost synergies from an integration could risk losing the scientists the acquisition is built around. Carrying an additional $36 billion in net new debt significantly reduces Pfizer’s flexibility to respond to new competitive threats, while an IRA-influenced pricing crackdown on ADCETRIS and future Seagen-developed products could directly impact the $10 billion revenue goal that justified this transaction's enormous premium over Seagen's market valuation.

# The approach taken in this paper views these issues as part of a connected system, consistent with ERM principles under the COSO (2017) and ISO 31000 frameworks, rather than discrete risks. This report builds on a number of prior analyses performed by the team: a SWOT analysis that adapts the “Better SWOT” framework developed by Fleisher and Bensoussan (2015), a qualitative assessment of perceived risks presented in risk register format with impacts and likelihoods quantified; a quantitative deep-dive using the Indicators & Warning (I&W) technique, alongside Monte Carlo simulation; and finally, recommendations on risk responses and the identification of relevant key risk indicators (KRIs). The report integrates, revises and extends these components into a comprehensive single assessment and incorporate specific instructor input and feedback provided at each stage. For example, the risk register was broadened from its initial set of 16, the KRIs' benchmarks were restated based on published benchmarks rather than the teams' estimations and an inconsistency between the ML heatmap and analyst risk assignments was rectified. The quantitative analysis procedure closely follows the step-by-step description by Khadem, Piya and Shamsuzzoha (2018), with risk values being transformed into numerical inputs used in Monte Carlo simulations, estimated as triangular distributions, validated using Monte Carlo simulation against qualitative risk priorities, and finally subjected to sensitivity analysis to identify key exposure drivers.

# Identification of Risks

All risks were surfaced through a structured SWOT Analysis of Pfizer's internal strengths and weaknesses and the external opportunities and threats associated with the acquisition of Seagen. The SWOT employed the Better SWOT Methodology, in accordance with Fleisher and Bensoussan (2015), framing it as an empirical analytical exercise rather than unstructured brain-dumping to ensure the results were future-looking, accurate, objective and actionable for risk analytics down the line. The individual threats and opportunities were each assessed across the following three criteria to qualify for admission into the risk register: 1) Does it have backing evidence of named competitors, stated deal size, or regulatory documents, versus general commentary of the industry; 2) Is there an observable leading indicator that can be used to track this risk,; and 3) Does this represent an independent risk driver, versus restatement of risk(s) already covered?

Sixteen risks were included in the original draft. Given instructor feedback that the register felt somewhat slim given the size of the transaction, 4 additional risks have been added based on themes identified during the SWOT Analysis that failed to migrate to the quantitative risk register; cybersecurity risk from the integration of systems, risk to ESG and reputational factors from post-acquisition workforce reductions, payer concentration risk and risk arising from purchasing group and individual contract concentration. This has resulted in a 20-risk registry in 5 broad categories of Strategic / Competitive; Operational; Financial; Legal / Regulatory; and Technology / Cyber. All twenty risks are summarized inTable 1with qualitative likelihood and impact ratings (1-10), resultant risk score (likelihood impact) and a final assigned priority level for each risk. Asterisk indicates newly identified risks not included in the previous submission to instructor.

| ID | Risk Description | Category | L | I | Score | Priority |
| --- | --- | --- | --- | --- | --- | --- |
| R-001 | Interest coverage ratio falling below safe levels due to acquisition debt load | Financial | 7 | 9 | 63 | High |
| R-002 | Failure to achieve $10B Seagen 2030 risk-adjusted revenue target | Financial | 7 | 9 | 63 | High |
| R-003 | IRA Medicare drug-price negotiations compress Seagen ADC revenue | Legal/Reg. | 8 | 8 | 64 | High |
| R-004 | FDA Complete Response Letter or labeling restriction on Seagen pipeline ADC submissions | Legal/Reg. | 6 | 7 | 42 | Medium |
| R-005 | Patent cliff and ADCETRIS biosimilar entry risk | Legal/Reg. | 6 | 8 | 48 | Medium |
| R-006 | Key ADC talent attrition from former Seagen organization | Operational | 8 | 9 | 72 | Critical |
| R-007 | ADC manufacturing scale-up failure at Seagen’s Bothell facility | Operational | 6 | 8 | 48 | Medium |
| R-008 | Clinical trial continuity disruption across Seagen’s 30+ active INDs | Operational | 5 | 7 | 35 | Medium |
| R-009 | IT systems and data harmonization cost overrun and timeline delay | Operational | 5 | 6 | 30 | Medium |
| R-010 | ADC combination therapy first-mover opportunity (positive risk) | Strategic | 7 | 8 | 56 | High |
| R-011 | Synergy realization shortfall against $1B target | Financial | 6 | 7 | 42 | Medium |
| R-012 | Goodwill impairment and DCF value erosion | Financial | 5 | 9 | 45 | Medium |
| R-013 | Free cash flow and dividend sustainability pressure | Financial | 6 | 8 | 48 | Medium |
| R-014 | Antitrust post-close compliance and FTC ongoing scrutiny | Legal/Reg. | 4 | 6 | 24 | Low |
| R-015 | Active litigation and ADC intellectual-property dispute risk | Legal/Reg. | 5 | 8 | 40 | Medium |
| R-016 | R&D pipeline integration disruption across 60 combined programs | Operational | 6 | 8 | 48 | Medium |
| R-017* | Cybersecurity breach or ransomware exposure during system integration | Technology | 6 | 9 | 54 | High |
| R-018* | ESG and reputational risk from post-acquisition workforce reduction | Strategic | 5 | 6 | 30 | Medium |
| R-019* | Payer and GPO concentration risk affecting ADC reimbursement | Financial | 5 | 7 | 35 | Medium |
| R-020* | Foreign-exchange exposure on ex-US ADC revenue and trial costs | Financial | 4 | 5 | 20 | Low |

Table 1. Group 10 enterprise risk register (1–10 scale; Risk Score = L × I). Priority bands: Low (1–29), Medium (30–49), High (50–69), Critical (70–100). Asterisks denote risks added in this submission.

## Newly Identified Risks and Their Justification

## R-017 (Cybersecurity breach during system integration). Pharm mergers are a favorite target for both ransomware groups and nation-state actors for precisely the reason that the time between signing and full integration yields a network seam that previously didn’t exist. The exposure at Pfizer and Seagen isn't limited to operations; Seagen's proprietary linker-payload technology -- the innovation that drove the $43 billion valuation -- is the precise sort of IP that enemies pursue exfiltration against. Once a SWOT but not included in quantitative analysis, it’s now added at Likelihood 6, Impact 9 to capture the impact of compromised clinical data or IP, even while the quarterly likelihood is only moderate.

## R-018 (ESG and reputational risk from workforce reduction). Pfizer will be chasing its $1 billion in synergies through facility consolidation and staffing reductions. Such workforce cuts attract public and investor ire at any time but especially so coupled with stock repurchases and will erode standing among ESG investors and patient-advocacy groups. Scored at Likelihood 5, Impact 6.

## R-019 (Payer and GPO concentration risk). Significant proportions of branded-oncology revenue in the US come via fewer than half dozen major health plan and hospital group purchasing organizations. If a leading payer restricts access or plays hardball on net pricing in the hospital or specialty-oncology channels that account for the majority of the Seagen product portfolio (a distinct risk from IRA in R-003) an incident could result in a substantial hit. Likelihood 5, Impact 7.

## R-020 (Foreign-exchange exposure). With both Seagen’s international trial network and the balance of Pfizer’s commercial-ex US footprint - which will become an even larger venue for the launch of Seagen products going forward - expect both cost and revenue translations. While relatively small at Likelihood 4, Impact 5, it warrants inclusion on the list of risks in play.

# References

Committee of Sponsoring Organizations of the Treadway Commission. (2017). Enterprise risk management: Integrating with strategy and performance. AICPA.

Fleisher, C. S., & Bensoussan, B. E. (2015). Business and competitive analysis: Effective application of new and classic methods (2nd ed.). Pearson Education.

Khadem, M. M. R. K., Piya, S., & Shamsuzzoha, A. (2018). Quantitative risk management in gas injection project: A case study from Oman oil and gas industry. Journal of Industrial Engineering International, 14(3), 637–654. https://doi.org/10.1007/s40092-017-0237-3

Liu, A. (2023, December 14). Done deal: Pfizer completes $43B acquisition of Seagen, doubling its oncology pipeline. Fierce Pharma. https://www.fiercepharma.com/pharma/done-deal-pfizer-completes-43b-acquisition-seagen-doubling-its-oncology-pipeline

Pfizer Inc. (2023a, March 13). Pfizer invests $43 billion to battle cancer [Press release]. https://www.pfizer.com/news/press-release/press-release-detail/pfizer-invests-43-billion-battle-cancer

Pfizer Inc. (2023b, December 14). Pfizer completes acquisition of Seagen [Press release]. https://www.pfizer.com/news/press-release/press-release-detail/pfizer-completes-acquisition-seagen