## Risk Register
Risk # | Date | The Risk of/That | Caused by | Resulting In | Consequence/Impact | Likelihood Score | Impact Score | Risk Score | Priority (H, M, L) | Mitigation | Risk Owner | Open/Closed
R-001 | 2026-05-31 | The risk of Pfizer not being able to gain meaningful market share within the ADCs in oncology space. | Competitors’ aggressive investments into ADC platforms through acquisitions and deals, such as AbbVie’s acquisition of ImmunoGen for $10.1B, Merck’s $4B+ deal to license ADC from Daiichi Sankyo, Bristol Myers Squibb’s $800M upfront deal, and Gilead’s advancements with Trodelvy, combined with deep scientific knowledge of ADCs among those competitors. | Reduction in the $10B in risk-adjusted Seagen revenue expected by 2030, reduction in the return on the $43B acquisition investment, increased payback period on the $31B in acquisition-related debt, and reduction in competitive standing in precision oncology. | Financial Impact: Estimated gap between the $3-5B required revenue in 2030, and projected revenue; potential loss in goodwill related to the Seagen transaction. Strategic Impact: First-mover advantage is lost with regard to ADCs; weakened negotiating position when securing licenses from outside firms. Operational Impact: Failure to maximize the production facilities located in Bothell, Washington. | 4 | 5 | 20 | H | 1) Develop ADC pipeline more quickly through an oncology integration office; 2) Develop strategic alliances for licensing through leading academic institutions and startups; 3) Targeted M&A of additional ADC platforms; 4) Competitive intelligence unit focusing on AbbVie, Merck, BMS, Gilead and Daiichi Sankyo; 5) Combination therapy advantage through clinical trial programs using Pfizer antibodies. | Chief Oncology Officer, Pfizer Oncology Division | Open
R-002 | 2026-05-31 | The risk of competition recruiting Seagen’s active pool of skilled ADC scientists, clinical development experts, and manufacturing experts during the period of integration. | Culture mismatch between a 3,400-person science-based company and an 80,000-person global organization, along with Pfizer’s ongoing cost realignment programs causing organizational instability, and the aggressive recruitment programs at ADC competitors such as AbbVie, Merck, Daiichi Sankyo, and BMS to address their scientific gaps. | Loss of critical ADC linker-payload technology expertise, increased timeframes for product development, delayed submissions of pipeline products to the FDA, transfer of proprietary technology expertise to the competition, and reduced scientific asset value of the $43B acquisition. | Operational Impact: Up to 6-12 months delay in achieving key milestones in the pipeline development process; increased costs associated with employee retention. Financial Impact: Added retention cost of $200-500M, plus missed out on opportunities; difficulty in meeting the estimated savings of $1B by 2026. Strategic Impact: Pipeline of competitors strengthened by Pfizer intellectual capital. | 4 | 4 | 16 | H | 1) Retention plans and equity for designated “critical talent” cohort; 2) Maintain independence of Seagen research-and-development leadership at Pfizer Oncology during an established transition period; 3) Non-solicitation agreements for Seagen employees and trade secret protection through legal enforcement mechanisms; 4) Culture alignment initiatives through working groups; 5) Executive sponsors linking top Pfizer executives to critical talent cohorts at Seagen; and 6) Monthly employee pulse surveys to identify declining engagement. | Chief Human Resources Officer, Integration Management Office | Open
R-003 | 2026-05-31 | The positive risk (opportunity) for Pfizer to establish first mover advantage in ADC combinations using the unique linker-payload platform in conjunction with the large Pfizer antibody library. | The synergy created by combining the post-acquisition strengths of Pfizer – with Seagen’s industry-leading linker-payload technology and Pfizer’s expansive portfolio of antibodies – provides an unmatched competitive advantage that no other competitor currently has in its entirety; each company holds a partial strength: AbbVie, Merck, BMS, and Gilead. | Unique differentiated next-generation ADC combination therapies, faster licensing revenues from academic and biotech partners, pricing power due to being first to market with combinations, improved FDA breakthrough therapy designation, and competitive advantage that cannot be duplicated by any competitor without its own antibody library. | Financial Impact: Added licensing/royalty revenue of up to $1-2B by 2030, beyond the $10B estimate of the Seagen forecast. Strategic Impact: Maintaining a competitive moat for a number of years ahead; preferred partner status with the top academic cancer institutions. Operational Impact: Increased usage of the existing infrastructure and faster clinical trial recruitment. | 3 | 4 | 12 | M | (1) Launch dedicated combination-therapy development unit within Pfizer Oncology organization; 2) Select 3–5 highly compelling antibody-Seagen payload combinations for expedited pre-clinical testing; 3) License and partner with MD Anderson, Memorial Sloan Kettering, and Dana Farber; 4) Early application to the FDA for breakthrough therapy and fast track designations; 5) Aggressive patent filings on new combination therapies; and 6) Investment from $1B synergy pool into combination therapies research and development. | Chief Scientific Officer, Oncology R&D | Open
s