There are three highest-priority risks from the previous qualitative and quantitative assessments. They are ADC market-share erosion, critical ADC talent poaching and first mover ADC combination opportunity.

1. ADC Market Share Erosion

Risk type: threat
Response strategy: mitigation or reduction 
Fitness of strategy: The competition in the ADC market cannot be avoided by Pfizer. Also, this risk cannot be transferred to other parties. Thus, the best response to reduce the probability and impact of the risk by faster monitoring and stronger commercial execution. 
Response: Pfizer could create an ADC competitive-response dashboard. The Integration Management Office, Oncology Commercial Team and Enterprise Risk Committee should review this dashboard monthly. The dashboard would track the number of ADC approvals and Phase 3 starts from competitors. Then, they should compare with Seagen’s ADC share trend and key product growth. The risk should be escalated if Seagen’s ADC share declines by more than 5% per year or if the number of competitor ADC approvals in a year is increasing.

The response plan would include faster medical-affairs supporter and stronger payer and reimbursement planning. Also, it would include more focused investment in the most competitive Seagen products.

2. Critical ADC Talent Poaching
Risk type: Threat
Response strategy: Mitigation or reduction 
Fitness of strategy: the risk should b reduced as the value of acquisition consists mainly of Seagen’s ADC scientists and senior oncology leaders. Pfizer cannot avoid the risk. The best strategy is to reduce risk by retaining key employees. 
Response Plan: Pfizer should identify key employees such as the most critical Seagen ADC scientists or clinical leaders. Also, it should run regular interviews with key employees to understand the incentives behind their leaving.

3. First-Mover ADC Combination Advantage
Risk type: Opportunity
Response strategy: Exploit 
Fitness of strategy: Pfizer should take this opportunity. The best response is to actively exploit the opportunity by moving quickly in ADC combination therapy before competitors take the lead.
Response plan: 
Pfizer should create a dedicated ADC combination Acceleration Team. The team will focus on identifying, testing and advancing new ADC combination programs.