## RiskRegister
RISK REGISTER — Pfizer Inc./Seagen Acquisition ¦ Group 10 ¦ Module 3 (Quantitative I&W Update) ¦ 16 Risks; quantitative assessment applied to 3 priority competitive risks — see 'Quant I&W Assessment' tab
Risk # | Date | The Risk of/That | Caused By | Resulting In | Consequence/Impact | Likelihood (1–10) | Impact (1–10) | Risk Score | Priority | Mitigation | Risk Owner | Status | Quant Probability (Monte Carlo) | Quant Impact P50 ($B) | Quant Impact P90 ($B) | Expected Loss/ Value ($B) | Quant Method | Key Indicator & Warning Trigger
R-001 | Jun 2026 | Interest coverage ratio falling below safe levels | Pfizer issued $31B long-term debt + $8B commercial paper to fund acquisition, nearly doubling total debt from $35.8B to $71.9B; 2023 interest coverage ratio only 1.48x | Under moderate stress (EBIT -20%, interest +10%) coverage drops to 1.08x; under severe stress (EBIT -35%, interest +15%) falls to 0.84x — below 1 indicating inability to service debt | Financial: Debt covenant breach risk. Credit: Moody's already downgraded A1→A2; S&P from A+→A. Operational: increased borrowing costs reduce capacity for pipeline investment. | 7 | 9 | 63 | High | Monthly interest coverage KRI (amber ≤1.2x; red ≤1.0x); accelerate FCF-based debt repayment; defer discretionary CAPEX if coverage approaches amber threshold. | CFO / Treasury | Open |  |  |  |  | Qualitative monitoring sufficient (Module 3 principle)
R-002 | Jun 2026 | Failure to achieve $10B Seagen 2030 revenue target | Base case assumes $8B from four marketed products + $2B from pipeline by 2030; stress testing shows a 10% revenue miss reduces DCF value from $44.19B to $39.77B; four products generated only $3.457B in 2025 — far below run-rate needed | Goodwill impairment on $17.1B Seagen goodwill allocation; reduced deal ROI on $43B acquisition; investor confidence loss and potential rating action | Financial: $17.1B goodwill impairment trigger if revenue miss sustained. Strategic: entire deal thesis dependent on pipeline execution + IRA headwinds. | 7 | 9 | 63 | High | Quarterly revenue vs. plan KRI (green ≥95%; amber 80–94%; red <80% for 2 consecutive quarters); accelerate ex-US commercialization; IRA scenario haircut in base model. | CFO / Chief Oncology Officer | Open |  |  |  |  | Qualitative monitoring sufficient (Module 3 principle)
R-003 | Jun 2026 | IRA Medicare drug-price negotiations compress Seagen ADC revenue | IRA price negotiation programme accelerating — 10 drugs 2026, 15 for 2027, 20/year from 2029; ADCETRIS approved 2011 approaching IRA eligibility; Third Circuit (May 2025) dismissed AstraZeneca's IRA challenge closing litigation pathway; MFN Executive Order (May 2025) adds additional pricing pressure layer | IRA net price haircuts of 25–60% on ADCETRIS or PADCEV reduce Seagen revenue by $1–3B against 2030 projection | Financial: $1–3B revenue reduction directly reduces deal ROI. Legal: No litigation pathway available following Third Circuit ruling. Strategic: Compressed margins reduce ADC pipeline reinvestment capacity. | 8 | 8 | 64 | High | Monthly IRA negotiation selection monitoring; proactive lifecycle management to reset exclusivity clock; government affairs engagement through PhRMA; IRA haircut scenarios in base financial model. | CFO / Government Affairs / Legal | Open |  |  |  |  | Qualitative monitoring sufficient (Module 3 principle)
R-004 | Jun 2026 | FDA Complete Response Letter (CRL) or labelling restriction on Seagen pipeline ADC submissions | Pfizer's combined 60-program oncology submission queue unusually large for single integration period; sigvotatug vedotin Phase 3 data anticipated 2025 with subsequent FDA review; PADCEV label expansion in progress; competing ADC submissions (Enhertu, Trodelvy) consume FDA reviewer capacity | 12–24 month approval delay per CRL; competitors establish clinical/commercial leadership in delayed indication; direct revenue deferral against $10B 2030 target | Regulatory: CRL requires resubmission — 12–24 month delay per programme. Commercial: Delayed label means deferred revenue and lost market share to competing ADCs. | 6 | 7 | 42 | Medium | Pre-submission Type B FDA meetings for all priority ADC programmes; comprehensive CMC packages for ADC-specific submissions; dedicated regulatory affairs resource for integration-period submission queue management. | Chief Regulatory Officer | Open |  |  |  |  | Qualitative monitoring sufficient (Module 3 principle)
R-005 | Jun 2026 | Patent cliff and ADCETRIS biosimilar entry risk | ADCETRIS approved 2011 — 12-year BPCIA exclusivity means biosimilar applicants could reference approval data from 2023–2026; paediatric exclusivity extension provides only 6-month buffer; TIVDAK, PADCEV, TUKYSA face exclusivity cliffs in 2030s — exactly when $10B target must be realized | Biosimilar entry compresses ADCETRIS pricing and market share before pipeline assets are ready to compensate; patent cliff distributed across 2026–2034 window | Financial: Biosimilar entry could reduce ADCETRIS/PADCEV combined revenue by $500M–$2B annually. Strategic: Pipeline revenue must compensate during same window Pfizer services acquisition debt. | 6 | 8 | 48 | Medium | Active continuation patent prosecution; new indication approvals to extend commercial exclusivity; forward-looking patent exclusivity calendar with biosimilar applicant monitoring at FDA. | Chief Legal Officer / Head of IP | Open |  |  |  |  | Qualitative monitoring sufficient (Module 3 principle)
R-006 | Jun 2026 | Key ADC talent attrition from former Seagen organization | Cultural friction between Seagen's 3,400-person entrepreneurial biotech and Pfizer's 80,000-person enterprise; active rival recruitment by AbbVie ($10.1B ImmunoGen), Merck ($4B+ Daiichi Sankyo); Array BioPharma (2019) precedent: significant scientist attrition within 18 months; 150–200 critical ADC scientists hold tacit linker-payload knowledge that does not transfer at deal close | Delayed clinical milestones; erosion of ADC linker-payload tacit knowledge; reduced pipeline productivity; pipeline attrition 20–30% increase (Munos, 2009) | Operational: 6–12 month FDA submission delays. Financial: $200–500M retention costs; each Phase 3 delay = $300–600M deferred revenue. Strategic: Departed scientists transfer proprietary know-how to competitors. | 8 | 9 | 72 | Critical | Critical talent retention equity program (24-month vesting); maintain Seagen R&D independence in Bothell; monthly attrition KRI (green ≤5%; amber 5–8%; red >8% annualized); executive sponsor program; non-solicitation protections. | CPO / Head of Oncology | Open | 55% | 0.65 | 0.95 | 0.37 | I&W indicators -> triangular probability; Monte Carlo (100k) on impact; EL = P x Impact | Annualized critical-scientist attrition; AbbVie/Merck recruitment activity. Trigger: attrition >8% (red), 5-8% (amber)
R-007 | Jun 2026 | ADC manufacturing scale-up failure at Seagen's Bothell facility | ADC manufacturing requires specialized cytotoxic HPAPI containment, precise conjugation chemistry, and DAR controls; Seagen facility designed for independent biotech scale — not Pfizer's global commercial demand for 4 approved products; Hospira precedent (2015): hundreds of millions in FDA remediation costs; $500M–$1B CAPEX expansion needed 2024–2028 | FDA 483 observations or warning letters; supply shortages for PADCEV/TUKYSA; direct revenue loss against $10B target | Operational: Each quarter of PADCEV/TUKYSA disruption = $200–400M deferred revenue. Regulatory: FDA 483 observations trigger mandatory remediation. Financial: $500M–$1B unplanned CAPEX if expansion delayed. | 6 | 8 | 48 | Medium | Independent manufacturing capacity audit within 90 days; $500M–$1B CAPEX expansion plan; backup CMO agreements for cytotoxic payload manufacturing; DAR consistency KRI monitoring. | COO / Head of Manufacturing | Open |  |  |  |  | Qualitative monitoring sufficient (Module 3 principle)
R-008 | Jun 2026 | Clinical trial continuity disruption across Seagen's 30+ active INDs | 30+ active IND applications require formal FDA sponsor-change process under 21 CFR Part 312; trial enrollment rates decline 18% in 6 months post-acquisition (JCO, 2019); CRO contract reassignment requires consent and renegotiation; Wyeth (2009) precedent: enrollment slowdowns required formal investigator communications program | 6-month enrollment disruption delays trial completion by 3–6 months; regulatory submission timelines pushed back; commercial launch dates for pipeline ADCs deferred | Regulatory: Sponsor-change filing errors create FDA compliance gaps. Financial: Each 6-month delay in Phase 3 ADC program = $300–600M deferred revenue against 2030 target. | 5 | 7 | 35 | Medium | Complete all FDA IND sponsor-change filings within 60 days; proactive investigator and patient communications affirming trial continuity; execute CRO contract reassignment within 90 days. | CMO / Regulatory Affairs | Open |  |  |  |  | Qualitative monitoring sufficient (Module 3 principle)
R-009 | Jun 2026 | IT systems and data harmonization cost overrun and timeline delay | Seagen: Oracle NetSuite ERP, Medidata Rave eDC, Veeva Vault RIM vs. Pfizer: SAP, internal eDC, Documentum; FDA guidance (21 CFR Part 11) prohibits mid-study eDC migration forcing dual-platform environment; Pharmacia (2003) precedent: 3+ years and significant budget overrun; Gartner benchmark: 36–48 months, $150–300M, 35–45% cost overrun probability | IT integration delays and cost overruns; dual-platform complexity increases submission error risk; regulatory data integrity gaps during migration | Financial: 35–45% probability of >20% cost overrun = up to $135M additional unplanned spend. Operational: Dual-platform maintenance increases clinical data management complexity and error risk. | 5 | 6 | 30 | Medium | Phased IT roadmap with parallel-run of Seagen clinical systems through Month 18; prohibit mid-study eDC migrations; maintain Veeva Vault RIM for active regulatory submissions until Documentum migration fully validated. | CIO / Head of Regulatory Affairs IT | Open |  |  |  |  | Qualitative monitoring sufficient (Module 3 principle)
R-010 | Jun 2026 | ADC combination therapy first-mover opportunity (Positive Risk) | Unique combination of Seagen's proprietary ADC linker-payload platform and Pfizer's extensive antibody library — no single competitor currently holds both; first-mover window estimated at 24–36 months before rivals close the gap through partnerships | First-mover leadership in ADC combination therapies for TNBC, mCRC, and HER2+ disease; $1–2B incremental licensing revenue above $10B Seagen forecast by 2030 | Financial: $1–2B incremental licensing/royalty revenue. Strategic: Durable combination-therapy moat. Reputational: Preferred partner with MD Anderson, Sloan Kettering, Dana-Farber. | 7 | 8 | 56 | High | ≥4 new ADC combination programs per quarter; academic/biotech partnerships; QoQ revenue tracking in new markets as KRI; monitor competitor partnership announcements as threat signal. | CSO / Head of Oncology Commercial | Open | 50% | 1.64 | 2.11 | 0.83 | I&W capture indicators -> triangular probability; Monte Carlo (100k) on upside; E[Value] = P x Upside | New ADC combo programs/qtr; academic partnership signings. Capture trigger: >=4 combo programs/qtr in 24-36 mo window
R-011 | Jun 2026 | Synergy realization shortfall against $1B target | Pfizer's $1B synergy target represents only 2.3% of $43B deal value — below the 3.2–4.1% achieved in comparable deals (AbbVie-Allergan 3.2%; BMS-Celgene 3.4–4.1%); synergies concentrated in manufacturing rationalization and SG&A reduction which conflict with Seagen R&D independence strategy | Synergy shortfall reduces financial justification for acquisition price; forces trade-off between cost-cutting and retaining Seagen's scientific culture — the very asset the deal acquired | Financial: Each $100M synergy shortfall reduces deal NPV by equivalent amount. Strategic: Aggressive cost-cutting to hit synergy target accelerates talent attrition (R-006), creating a self-defeating feedback loop. | 6 | 7 | 42 | Medium | Quarterly synergy tracking dashboard vs. $1B target by 2026; ring-fence R&D headcount from synergy program; benchmark synergy realization against AbbVie-Allergan and BMS-Celgene milestones. | CFO / COO | Open |  |  |  |  | Qualitative monitoring sufficient (Module 3 principle)
R-012 | Jun 2026 | Goodwill impairment and DCF value erosion | Pfizer allocated $17.148B of the $43B acquisition price to goodwill; DCF model shows deal value of $44.19B under base case, $39.77B under 10% revenue stress, and $34.62B under 20% stress — implying a potential $9.57B value destruction scenario | Goodwill impairment charge on Pfizer's income statement; investor confidence loss; credit rating pressure from asset write-down | Financial: A 20% revenue miss scenario implies $9.57B impairment — nearly 13% of the original deal value. Accounting: Under ASC 350, goodwill must be tested annually; any indicator of impairment triggers immediate write-down. | 5 | 9 | 45 | Medium | Annual goodwill impairment testing with quarterly indicators review; maintain DCF sensitivity dashboard (base/stress/upside scenarios); escalate to Board Audit Committee if revenue tracking below stress threshold for 2 consecutive quarters. | CFO / Chief Accounting Officer | Open |  |  |  |  | Qualitative monitoring sufficient (Module 3 principle)
R-013 | Jun 2026 | Free cash flow and dividend sustainability pressure | Pfizer's dividend coverage fell below 1x in 2025–2026 — paying out more in dividends than it earns in adjusted EPS; $31B acquisition debt service consumes FCF that previously supported dividends and buybacks; cost-cutting programs insufficient to fully offset COVID revenue decline and acquisition interest costs | Dividend cut risk — first in decades — which would trigger institutional investor selling and significant share price decline; reduced FCF constrains pipeline investment and M&A optionality | Financial: Dividend cut would trigger forced selling by income-oriented institutional shareholders. Strategic: Reduced FCF limits Pfizer's ability to execute further pipeline-filling acquisitions while servicing acquisition debt. | 6 | 8 | 48 | Medium | Monthly FCF vs. dividend coverage ratio monitoring (amber <1.1x; red <1.0x); model dividend sustainability under IRA stress scenarios; evaluate dividend growth suspension vs. cut as tactical options. | CFO / Board Finance Committee | Open |  |  |  |  | Qualitative monitoring sufficient (Module 3 principle)
R-014 | Jun 2026 | Antitrust post-close compliance and FTC ongoing scrutiny | FTC required Pfizer to irrevocably donate all U.S. Bavencio (avelumab) royalties to the AACR as a condition of deal approval; 2023 DOJ/FTC updated Merger Guidelines create heightened scrutiny framework for future pharma M&A; Pfizer's ambition to execute further ADC bolt-on acquisitions (per JPM 2024 Boshoff comments) faces increased regulatory overhang | Ongoing Bavencio royalty donation obligation reduces FCF; future M&A pipeline-filling strategy faces heightened FTC scrutiny and potential blocking; compliance failure triggers investigation risk | Financial: Bavencio royalty stream permanently diverted — reduces long-term FCF. Strategic: Heightened FTC scrutiny constrains Pfizer's ability to execute bolt-on ADC acquisitions needed to fill post-Seagen pipeline gaps. | 4 | 6 | 24 | Low | Dedicated antitrust compliance monitoring for Bavencio obligation; early FTC engagement process for any future acquisitions >$500M; antitrust counsel review of all future M&A targets. | Chief Legal Officer / Government Affairs | Open |  |  |  |  | Qualitative monitoring sufficient (Module 3 principle)
R-015 | Jun 2026 | Active litigation and ADC IP dispute risk | Seagen lost a significant patent dispute to Daiichi Sankyo in 2022 related to ADC linker-payload technology; auristatin platform (underlying ADCETRIS and PADCEV) faces ongoing IP challenges; product liability exposure from cytotoxic ADC payloads causing serious adverse events; Pfizer inherited all active litigation at deal close | Successful IP challenge could invalidate core ADC technology underlying multiple Seagen products; product liability verdict could trigger market withdrawal and reputational damage | Legal: IP invalidation of auristatin platform would remove foundation of ADCETRIS and PADCEV commercial franchises. Financial: Product liability verdict could expose Pfizer to hundreds of millions in damages plus mandatory recall costs. | 5 | 8 | 40 | Medium | Comprehensive IP audit of all inherited Seagen patent portfolio within 90 days of close; continuation prosecution strategy to strengthen patent positions; product liability reserve adequacy review; monitor auristatin challenge proceedings. | Chief Legal Officer / Head of IP Litigation | Open |  |  |  |  | Qualitative monitoring sufficient (Module 3 principle)
R-016 | Jun 2026 | R&D pipeline integration disruption across 60 combined programs | Portfolio rationalization, resource reallocation, and governance conflicts during 24-month integration period; pipeline attrition rates increase 20–30% in 24 months post-acquisition (Munos, 2009); Wyeth (2009) precedent: bapineuzumab flagship program cancelled; Medivation (2016): governance conflicts over oncology pipeline prioritization | 12–18 program cancellations or delays from combined 60-program pipeline during 2024–2026 window; deferred revenue; missed regulatory submission deadlines | Financial: Each Phase 3 ADC program cancellation = $300–600M lost development investment and deferred revenue. Strategic: Pipeline momentum lost before $10B 2030 target is established. | 6 | 8 | 48 | Medium | Dedicated IMO with 90-day portfolio review mandate; ring-fence late-stage Seagen ADC programs from routine rationalization cycle; maintain Seagen R&D decision-making independence in Bothell. | CSO / IMO Lead | Open |  |  |  |  | Qualitative monitoring sufficient (Module 3 principle)
Note on N8: Source: Group10_M3_Quant_IW_MonteCarlo.ipynb (Monte Carlo, 100k iter, seed 42); inputs iw_montecarlo_inputs.csv
Note on N12: Source: Group10_M3_Quant_IW_MonteCarlo.ipynb (Monte Carlo, 100k iter, seed 42); inputs iw_montecarlo_inputs.csv

## Quant I&W Assessment
QUANTITATIVE RISK ASSESSMENT — Indicators & Warning (I&W) + Monte Carlo ¦ Group 10 ¦ Module 3 ¦ Three priority competitive risks
Risk ID | Risk | Type | Qual L (1-10) | Qual I (1-10) | Qual Score | Key I&W Indicator(s) | Warning Trigger / Threshold | Quant Probability (Monte Carlo) | Impact P50 ($B) | Impact P90 ($B) | Expected Loss/ Value ($B) | Scenario VaR P90 ($B) | Quant Method | Data Source
R-MSE | ADC market-share erosion | Threat | 7 | 9 | 63 | Approvals for competitor ADCs, Phase 3 initiation; Seagen ADC share trajectory; Enhertu vs Padcev growth trend; IRA price impacts | Seagen ADC share decline >5%/yr OR >=3 competitor ADC approvals/yr | 53.3% | 4.86 | 7.48 | 2.66 | 6.67 | I&W indicators -> triangular probability; Monte Carlo (100k) on revenue/value impact | ClinicalTrials.gov; Drugs@FDA; SEC EDGAR; Group 10 DCF model
R-006 | Critical ADC talent poaching | Threat | 8 | 9 | 72 | Attrition of key scientist (annualized); rival hiring (AbbVie, Merck); acceptance rate of retention offers; fill time | Annualized attrition >8% (red); 5-8% (amber) | 55% | 0.65 | 0.95 | 0.37 | 0.87 | I&W indicators -> triangular probability; Monte Carlo (100k) on retention + delay impact | Array BioPharma 2019 precedent; Munos 2009; Risk Register R-006
R-010 | First-mover ADC combination advantage | Opportunity | 7 | 8 | 56 | Number of new ADC combos programmed each quarter, academic partnership signings, competitor partnership announcement (as a signal of threats). | Capture trigger: >=4 new combo programs/qtr within 24-36 month window | 50% | 1.64 | 2.11 | 0.83 | 1.95 | I&W capture indicators -> triangular probability; Monte Carlo (100k) on upside value | Risk Register R-010; MD Anderson/Sloan Kettering/Dana-Farber pipeline
Portfolio note: Net expected position of the three priority risks = threats (R-MSE + R-006) expected loss ~$3.03B offset by R-010 expected upside ~$0.83B. Figures are mean of P x Impact from 100,000 Monte Carlo iterations (seed 42).