## Risk Response Planning Pfizer–Seagen Acquisition

Group 10 | ALY6130 Risk Management Analytics

### Our Approach

We pulled the four highest-priority risks from our Module 2 and 3 work the ones that scored highest on the heat map and carried the biggest expected losses in the Monte Carlo model and built a practical response plan for each one.

### Risk 1: ADC Market-Share Erosion (R-MSE)

Score: 20 | Expected Loss: $2.66B | Strategy: Mitigation

Avoidance is off the table the entire acquisition thesis is built on competing in the ADC space. Transfer does not work either since you cannot insure against a competitor winning a clinical trial. That leaves mitigation, and the window to act is narrow.

The competitive landscape is moving fast. AbbVie, Merck, BMS, and Gilead are all building ADC positions right now, during the same 18–24 months that Pfizer is distracted by integration. The response is to compress that window in Pfizer's favour accelerate PADCEV's first-line label expansion, build payer relationships for pipeline candidates 18 months before approval, and lock in academic partnerships at MD Anderson, Dana-Farber, and Sloan Kettering to generate real-world evidence rivals cannot easily replicate.

Owner: Chief Commercial Officer KRI trigger: >5% annual share decline or ≥3 competitor approvals per year → escalate to ERC

### Risk 2: Cybersecurity Breach During Integration (R2)

Score: 20 | Strategy: Mitigation + Transfer

Integration is not optional, so avoidance is not either. But the exposure window is time-bounded it runs from close through full system consolidation and most of it is within Pfizer's control. That makes mitigation the right primary strategy, with cyber insurance covering whatever residual risk remains.

In practice this means zero-trust segmentation between Pfizer and Seagen environments from day one, all Seagen logs feeding into Pfizer's SOC within 30 days, MFA enforced across all inherited accounts within 60 days, and a tabletop exercise specifically designed around ADC IP theft during a migration event not a generic drill. Cyber insurance should explicitly cover integration-period events and third-party vendor breaches.

Owner: CISO / Privacy Officer KRI trigger: Any critical vulnerability open >30 days or unresolved ePHI anomalies → immediate escalation

### Risk 3: Critical ADC Talent Poaching (R-006)

Score: 16 | Expected Loss: $0.37B | Probability: 55% | Strategy: Mitigation

Transfer is not applicable and acceptance is not defensible at 55% probability especially given what happened after the Array BioPharma acquisition in 2019, when Pfizer underestimated exactly this risk and paid for it. The root causes here are all addressable: cultural disruption, loss of scientific autonomy, and ambiguity about what a career at Pfizer looks like for a Seagen scientist.

The response starts with a named Critical Role List of the 150–200 scientists whose departure would damage the deal thesis, backed by tiered retention awards vesting over 36 months. Just as importantly, Seagen's R&D identity needs to be visibly preserved a recognisable ADC Centre of Excellence with its own leadership structure for at least 24 months. Quarterly stay interviews, not exit interviews, keep the early warning system live.

Owner: CHRO / Oncology R&D Leadership KRI trigger: Attrition >5% (amber) or >10% (red) → retention plan review

### Risk 4: IRA Drug Pricing Exposure (R2-B)

Score: 16 | Strategy: Acceptance + Mitigation

This one is different from the others. The Third Circuit's May 2025 ruling shut down the litigation pathway CMS drug price negotiation is now a permanent feature of the market, not a policy uncertainty to wait out. ADCETRIS, approved in 2011, is likely heading into a negotiation cycle, and Pfizer needs to plan for a 15–50% net price haircut rather than hoping the policy changes.

Acceptance does not mean doing nothing. The mitigation layer is about reducing how much of the portfolio is exposed pursuing new indications and paediatric extensions for ADCETRIS to extend exclusivity, shifting toward value-based payer contracts, and building the MFN Executive Order into the financial stress scenarios alongside the IRA base case. The revenue projection presented to the Board should already reflect IRA assumptions, not the pre-2022 number.

Owner: CFO / Government Affairs / Commercial Oncology KRI trigger: CMS selection of ADCETRIS or PADCEV for negotiation → immediate Board-level review

### Summary Table

| Risk | Score | Strategy | Key Action |
| --- | --- | --- | --- |
| ADC Market-Share Erosion | 20 | Mitigation | Accelerate launches; lock in payer & academic partnerships |
| Cybersecurity Breach | 20 | Mitigation + Transfer | Zero-trust from day one; cyber insurance for residual risk |
| ADC Talent Poaching | 16 | Mitigation | Critical Role List; 36-month retention awards; preserve Seagen identity |
| IRA Pricing Exposure | 16 | Acceptance + Mitigation | Rebuild revenue model with IRA haircut; lifecycle management |